## Sheet1
Week | CI/CD pipeline | Estimates | Estimation of Difficulty
2022-09-05 | Setup Github Repository and move code to it | Half week | 2
2022-09-12 | Setup Github actions to install dependencies, linting and unit testing | One week | 3
2022-09-19 | Connect Github repo with Azure Pipelines | One week | 5
2022-09-26 | Setup CD process | One week | 5
2022-10-03
2022-10-10
2022-10-17
2022-10-24
2022-10-31
2022-11-07
2022-11-14
2022-11-21
| Quarterly Goals | Annual Goals
| Setup CI | Setup Alarms
Setup CD